## User stories
| Main User Story | Sub-Task
1 | Theatre | Add Theatre
Delete Theatre
2 | screen | Add Screen
Delete Screen
Update Screen
3 | Show | Delete Show
Add Show
4 | Movie | Add Movie
Delete Movie
5 | Booking | add booking
delete booking
view booking
update booking
add n delete ticket
6 | Seat | add seat
book seat
cancel seat
7 | Authentication | login
logout

## Naveen
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Theatre
1.1 | Add Theatre
1.1.1 | Html Page | 3
1.1.2 | Component | 1 | 1 | 2020-08-04
1.1.3 | Validations + Exception Handling | 1.5 | 2 | 2020-08-04
1.2 | Delete Theatre
1.2.1 | Html Page | 1
1.2.2 | Component | 1 | 1 | 2020-08-04
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-04
2 | Screen
2.1 | Add movie
2.1.1 | Html Page | 2
2.1.2 | Component | 1.5 | 1.5 | 2020-08-10
2.1.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-10
2.2 | Delete movie
2.2.1 | Html Page | 1
2.2.2 | Component | 1 | 1 | 2020-08-10
2.2.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-10
2.3 | Search movie
2.3.1 | Html Page | 2
2.3.2 | Component | 2 | 2 | 2020-08-10
2.3.3 | Validation | 1 | 1 | 2020-08-10

## Bhavani
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Show
1.1 | Add show
1.1.1 | Html Page | 2
1.1.2 | Component | 1 | 1 | 2020-08-04
1.1.3 | Validations + Exception Handling | 2 | 2 | 2020-08-04
1.2 | Delete show
1.2.1 | Html Page | 1
1.2.2 | Component | 1 | 1 | 2020-08-04
1.2.3 | Validations + Exception Handling | 0.5 | 0.5 | 2020-08-04
1.3 | add Screen
1.3.1 | Html Page | 1
1.3.2 | Component | 1 | 1 | 2020-08-10
1.3.3 | Validations + Exception Handling | 3 | 3 | 2020-08-10
1.4 | delete Screen
1.4.1 | Html Page | 1
1.4.2 | Component | 1 | 1 | 2020-08-10
1.4.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-10
1.5 | Update Screen
1.5.1 | Html Page | 1
1.5.2 | Component | 1 | 1 | 2020-08-10
1.5.3 | Validations + Exception Handling | 1 | 1 | 2020-08-10

## Shirisha
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Booking
1.1 | Add booking
1.1.1 | HTML Page | 3
1.1.2 | Component | 1 | 1 | 2020-08-04
1.1.3 | Validations + Exception Handling | 2 | 2 | 2020-08-04
1.2 | delete booking
1.2.1 | HTML Page | 3
1.2.2 | Component | 1.5 | 1.5 | 2020-08-04
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-04
1.3 | add ticket
1.3.1 | HTML Page | 2
1.3.2 | Component | 1.5 | 1.5 | 2020-08-10
1.3.3 | Validations + Exception Handling | 2 | 2 | 2020-08-10
1.4 | show ticket
1.4.1 | HTML Page | 2
1.4.2 | Component | 1 | 1 | 2020-08-10
1.4.3 | Validations + Exception Handling | 2 | 2 | 2020-08-10
1.5 | view and update booking
1.5.1 | HTML page | 1
1.5.2 | Component | 1 | 1 | 2020-08-10
1.5.3 | Validations + Exception Handling | 1 | 1 | 2020-08-10

## Tejasri
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Alloted on day | Comments
1 | Movie
1.1 | Add Seat
1.1.1 | HTML page | 3
1.1.2 | Component | 1 | 1 | 2020-08-04
1.1.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-04
1.2 | Delete Seat
1.2.1 | HTML page | 2
1.2.2 | Component | 1.5 | 1.5 | 2020-08-04
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-04
1.3 | Search Movie
1.3.1 | HTML Page | 2
1.3.2 | Component | 1.5 | 1.5 | 2020-08-10
1.3.3 | Validation + Exception Handling | 1.5 | 1.5 | 2020-08-10
2 | Seat
2.1 | Block Seat
2.1.1 | HTML Page | 3
2.1.2 | Component | 2.5 | 2.5 | 2020-08-10
2.1.3 | Validation + Exception Handling | 1 | 1 | 2020-08-10
2.2 | Book Seat
2.2.1 | HTML Page | 2
2.2.2 | Component | 1 | 1 | 2020-08-10
2.2.3 | Validation + Exception Handling | 2 | 2 | 2020-08-10
2.3 | Cancel Seat
2.3.1 | HTML Page | 1
2.3.2 | Component | 2
2.3.3 | Validation + Exception Handling | 2